## Current Week
Tasks Sprint 4 | Status of Task | Members | Tasks To-Do | Tasks also worked on / did research on | Total Hours for the week/sprint | 2023-12-04 | Hours | 2023-12-05 | Hours | 2023-12-06 | Hours | 2023-12-07 | Hours | 2023-12-08 | Hours | 2023-12-09 | Hours | 2023-12-10 | Hours
Work on redesigning the charts to how our client would find them useful. | Completed | Alex | Tasks 1,2,18,19 | Tasks 3, 4, 10, 11, 20 | 4.5 | Made new timesheet for the final week Worked on making sure all documentation was ready to be submitted for sprint 4 and made sure that all documentation was ready for the progress check Fixed a small bug with the budget report. Budget report now displays correctly | 3.5 | Meeting with Corrine to show the final product. Inclass Progress Check | 1
Add charts to the visual tab of a grant subpage. Test to make sure they can still be downloaded as a pdf. | Completed | Chase | Tasks 5,6, 18 | Task 19 | 1 |  |  | Meeting with Corrine to show the final product. Inclass Progress Check | 1
Make a pie chart that will be placed on the main tab. | Completed | Daron | Tasks 7,8,9,13,21 | Task 5 | 1 |  |  | Meeting with Corrine to show the final product. Inclass Progress Check | 1
Make all data for the charts come from the database | Completed | Ken | Tasks 3,10,11,19 | Task 14, 18 | 1 |  |  | Meeting with Corrine to show the final product. Inclass Progress Check | 1
Work on adding backend functionality to allow our client to change thier password. | Completed
Implement the calender component on the show page of a grant subpage | Completed
Work on implementing frontend functionality to create a grant | Completed
Work on implementing frontend functionality to edit an exisiting grant or newly created grant | In progress
Work on implementing frontend functionality to delete an existing grant or newly created grant | Completed
Work on the layout of the grant main tab | Completed
Work on creating the internal transactions system | Completed
Work on email notifcations when some sort of change happens on the website | Not started
Work on refactoring the frontend and setup redux | Completed But Scrapped
Work on creating an employee dashboard page | Not started
Work on editing an employee's information | Not started
Work on deleting an employee | Not started
Work on the editing of the grant flow | Not started
Work on the making the different types of reports related to a grant | Completed
Work on making controller end points necessary for grants | Completed
Importing of a CSV file by a user | Scrapped
Worked on setting up recoil so that backend data can be easily passed to frontend | Completed

## Week of 1127
Tasks Sprint 4 | Status of Task | Members | Tasks To-Do | Tasks also worked on / did research on | Total Hours for the week/sprint | 2023-11-27 | Hours | 2023-11-28 | Hours | 2023-11-29 | Hours | 2023-11-30 | Hours | 2023-12-01 | Hours | 2023-12-02 | Hours | 2023-12-03 | Hours
Work on redesigning the charts to how our client would find them useful. | Completed | Alex | Tasks 1,2,18,19 | Tasks 3, 4, 11, 20 | 20.5 | Fixed up timesheet from the Thanksgiving week and made new timesheet for the week Worked on adding functionality for the charts to display transactions correctly (transactions for each month are now calculated correctly) Added transaction data and grant budget items data to the database for grant 1 (Amy Cook grant) Fixed MoneySpent calculation error for the grant dashboard Fixed Main Tab pie chart so that money spent and money remaining corresponds with grant dashboard | 4 | Capstone Class/Meeting Time Performed think Aloud with Finch Team Worked on adding functionality for the charts to display transactions correctly (hook, endpoints, state, visual tab) | 4 | Transactions for each month are now displayed appropriately in the bar and line charts. Visual Tab completed Changes to the bar and line charts were made so that these transactions were displayed correctly. Fixed an error with the hook related to getting the transactions | 5 | Capstone Class/Meeting Time | 2 |  |  | Helped out Chase with getting the labor tab for a grant functional | 1 | Added data to the backend relating to a labor report. Fixed an error on the frontend so that the rate and earnings code was not undefined Worked on making the budget report functional | 4.5
Add charts to the visual tab of a grant subpage. Test to make sure they can still be downloaded as a pdf. | Completed | Chase | Tasks 5,6, 18 | Task | 9 |  |  | Capstone Class/Meeting Time Performed think Aloud with Finch Team | 2 |  |  | Capstone Class/Meeting Time | 2 |  |  | Reviewed new hook changes to labor tab Implemented labor tab functionality | 5
Make a pie chart that will be placed on the main tab. | Completed | Daron | Tasks 7,8,9,13,21 | Task 5 | 4 |  |  | Capstone Class/Meeting Time Performed think Aloud with Finch Team | 2 |  |  | Capstone Class/Meeting Time | 2
Make all data for the charts come from the database | Completed | Ken | Tasks 3,10,11,19 | Task 14 | 13 |  |  | Capstone Class/Meeting Time Performed think Aloud with Finch Team | 2 |  |  | Capstone Class/Meeting Time | 2 |  |  | Assisted Chase with the development of the labor tab | 5 | Worked on making the effort report | 4
Work on adding backend functionality to allow our client to change thier password. | Completed
Implement the calender component on the show page of a grant subpage | Completed
Work on implementing frontend functionality to create a grant | Completed
Work on implementing frontend functionality to edit an exisiting grant or newly created grant | In progress
Work on implementing frontend functionality to delete an existing grant or newly created grant | Completed
Work on the layout of the grant main tab | Completed
Work on creating the internal transactions system | In progress
Work on email notifcations when some sort of change happens on the website | Not started
Work on refactoring the frontend and setup redux | Completed But Scrapped
Work on creating an employee dashboard page | Not started
Work on editing an employee's information | Not started
Work on deleting an employee | Not started
Work on the editing of the grant flow | Not started
Work on the making the different types of reports related to a grant | In progress
Work on making controller end points | In progress
Importing of a CSV file by a user | Scrapped
Worked on setting up recoil so that backend data can be easily passed to frontend | Completed

## Week of 1120
Tasks Sprint 4 | Status of Task | Members | Tasks To-Do | Tasks also worked on / did research on | Total Hours for the week/sprint | 2023-11-20 | Hours | 2023-11-21 | Hours | 2023-11-22 | Hours | 2023-11-23 | Hours | 2023-11-24 | Hours | 2023-11-25 | Hours | 2023-11-26 | Hours
Work on redesigning the charts to how our client would find them useful. | Completed | Alex | Tasks 1,2,18,19 | Tasks 4, 11, 20 | 7 | Made new timesheet for the week Installed and setup Insomnia to test backend transactions and grant buget item functions. Found errors in both the transaction and grant budget item functions and fixed them. (Also fixed the respective routes) Added data in the database for transactions and grant budget items | 3 | Capstone Class/Meeting Time Changed Think Aloud Documentation Added money spent on a grant (on grant dashboard) via transactions (in the database) Discussed the final things left to implement | 4
Add charts to the visual tab of a grant subpage. Test to make sure they can still be downloaded as a pdf. | Completed | Chase | Tasks 5,6, 18 | Task | 4 | tested branches before merging to Main | 1 | Capstone Class/Meeting Time Discussed the final things left to implement | 3
Make a pie chart that will be placed on the main tab. | Completed | Daron | Tasks 7,8,9,13,21 | Task 5 | 8 | Worked on allowing a user to create a grant Made delete functionality for grants on the frontend | 5 | Capstone Class/Meeting Time Discussed the final things left to implement | 3
Make all data for the charts come from the database | In progress | Ken | Tasks 3,10,11,19 | Task | 9 | worked on employee and pi grids on main page | 6 | Capstone Class/Meeting Time Helped Alex with adding money spent amount via transactions to the frontend grant dashboard Discussed the final things left to implement | 3
Work on adding backend functionality to allow our client to change thier password. | Completed
Implement the calender component on the show page of a grant subpage | Completed
Work on implementing frontend functionality to create a grant | Completed
Work on implementing frontend functionality to edit an exisiting grant or newly created grant | In progress
Work on implementing frontend functionality to delete an existing grant or newly created grant | Completed
Work on the layout of the grant main tab | Completed
Work on creating the internal transactions system | In progress
Work on email notifcations when some sort of change happens on the website | Not started
Work on refactoring the frontend and setup redux | Completed But Scrapped
Work on creating an employee dashboard page | Not started
Work on editing an employee's information | Not started
Work on deleting an employee | Not started
Work on the editing of the grant flow | Not started
Work on the making the different types of reports related to a grant | In progress
Work on making controller end points | In progress
Importing of a CSV file by a user | In progress
Worked on setting up recoil so that backend data can be easily passed to frontend | Completed

## Week of 1113
Tasks Sprint 4 | Status of Task | Members | Tasks To-Do | Tasks also worked on / did research on | Total Hours for the week/sprint | 2023-11-13 | Hours | 2023-11-14 | Hours | 2023-11-15 | Hours | 2023-11-16 | Hours | 2023-11-17 | Hours | 2023-11-18 | Hours | 2023-11-19 | Hours
Work on redesigning the charts to how our client would find them useful. | Completed | Alex | Tasks 1,2,18,19 | Tasks 4, 11, 20 | 15.5 | Created the new timesheet for the week Worked on the redesign of the bar chart. | 3 | Capstone Class/Meeting Time Worked on making the get transaction and create transaction logic (Backend wise) | 4 | Made sure that all documentation was ready to be shown for the progress check | 2.5 | Capstone Class/Meeting Time Worked on making a function in the grant controller for transactions | 3 |  |  | Worked on making necessary transaction functions and worked on fixing the formating of the bar and line graphs Did research on allowing a user to import a CSV that would display the information in it. | 3
Add charts to the visual tab of a grant subpage. Test to make sure they can still be downloaded as a pdf. | Completed | Chase | Tasks 5,6, 18 | Task | 9 |  |  | Capstone Class/Meeting Time Worked on the different types of reports | 4 |  |  | Capstone Class/Meeting Time | 2 |  |  |  |  | Setting up labor report tab | 3
Make a pie chart that will be placed on the main tab. | Completed | Daron | Tasks 7,8,9,13,21 | Task 5 | 10 | Worked on the create grant form and controller logic | 4 | Capstone Class/Meeting Time Worked on allowing a user to create a grant (worked on the form so that a user could input this data) | 4 |  |  | Capstone Class/Meeting Time | 2
Make all data for the charts come from the database | Completed | Ken | Tasks 3,10,11,19 | Task | 10 | reviewd PR's, discussed issues with team | 3 | Capstone Class/Meeting Time Helped Alex with making endpoints related to transactions (outlined what there was to do next in terms of the transactions) Worked on adding elements to the main tab on a grant show page | 3 | reviewed documentation, helped team plan out technical solutions to features | 1 | Capstone Class/Meeting Time helped team plan out functions for transactions, create grant, others | 3
Work on adding backend functionality to allow our client to change thier password. | Completed
Implement the calender component on the show page of a grant subpage | Completed
Work on implementing frontend functionality to create a grant | In progress
Work on implementing frontend functionality to edit an exisiting grant or newly created grant | In progress
Work on implementing frontend functionality to delete an existing grant or newly created grant | Completed
Work on the layout of the grant main tab | Completed
Work on creating the internal transactions system | In progress
Work on email notifcations when some sort of change happens on the website | Not started
Work on refactoring the frontend and setup redux | Completed But Scrapped
Work on creating an employee dashboard page | Not started
Work on editing an employee's information | Not started
Work on deleting an employee | Not started
Work on the editing of the grant flow | Not started
Work on the making the different types of reports related to a grant | In progress
Work on making controller end points | In progress
Importing of a CSV file by a user | In progress
Worked on setting up recoil so that backend data can be easily passed to frontend | Completed

## Week of 116
Tasks Sprint 4 | Status of Task | Members | Tasks To-Do | Tasks also worked on / did research on | Total Hours for the week/sprint | 2023-11-06 | Hours | 2023-11-07 | Hours | 2023-11-08 | Hours | 2023-11-09 | Hours | 2023-11-10 | Hours | 2023-11-11 | Hours | 2023-11-12 | Hours
Work on redesigning the charts to how our client would find them useful. | In progress | Alex | Tasks 1,2,3 | Tasks 4 | 13 | Due to a lack of memory on current laptop, I had to set everything up on a different computer to run the code. | 1 | Capstone Class/Meeting Time Made a new timesheet and outlined all tasks that need to be completed this sprint. Helped Ken with making the Project Board | 5 |  |  | Capstone Class/Meeting Time Worked on the redesigning of the bar and line chart Had a meeting with Corrine | 3 |  |  | Worked on the redesign of the line chart. Values such as the start data and end date were pulled from the database so that the correct amount of months can be displayed. Total amount of a grant was also pulled from the database so that the burn rate can be calculated properly. | 4
Add charts to the visual tab of a grant subpage. Test to make sure they can still be downloaded as a pdf. | Completed | Chase | Tasks 5,6 | Task | 11 |  |  | Capstone Class/Meeting Time Got the Calander Component Working Moved charts from Main tab to Visuals Added Calendars to Visuals tab | 4 | Set up data grid structure for Budget tab | 1 | Capstone Class/Meeting Time Had a meeting with Corrine | 3 |  |  | Getting change password functional | 2 | Worked on Labor/Budget reports | 1
Make a pie chart that will be placed on the main tab. | In progress | Daron | Tasks 7,8,9,13,21 | Task | 16 |  |  | Capstone Class/Meeting Time Worked on refactoring and did research on redux. Worked on installing redux | 5 | Worked on implementing redux feature for database calls but kept running into problems. Also tried to implement a react-query feature (but realized this would only be benefical if our app was a server sided app) Performed research on recoil | 3 | Capstone Class/Meeting Time Installed the recoil feature in our app and database calls works as intended. Had a meeting with Corrine | 3 |  | 3 | Helped Chase with change password fixes | 2
Make all data for the charts come from the database | In progress | Ken | Tasks 10,11,19 | Task | 11 |  |  | Capstone Class/Meeting Time Helped Chase get Calander component working Helped Alex with making the Project Board | 5 |  |  | Capstone Class/Meeting Time Had a meeting with Corrine | 3 |  |  | did all endpoints for two models and created all types | 3
Work on adding backend functionality to allow our client to change thier password. | In progress
Implement the calender component on the show page of a grant subpage | Completed
Work on implementing frontend functionality to create a grant | In progress
Work on implementing frontend functionality to edit an exisiting grant or newly created grant | In progress
Work on implementing frontend functionality to delete an existing grant or newly created grant | In progress
Work on the layout of the grant main tab | In progress
Work on creating the internal transactions system | In progress
Work on email notifcations when some sort of change happens on the website | Not started
Work on refactoring the frontend and setup redux | In progress
Work on creating an employee dashboard page | Not started
Work on editing an employee's information | Not started
Work on deleting an employee | Not started
Work on the editing of the grant flow | Not started
Work on the making the different types of reports related to a grant | In progress
Work on making controller end points | In progress
Worked on setting up recoil so that backend data can be easily passed to frontend | In progress

## Week of 1030
Tasks Sprint 3 | Status of Task | Members | Tasks To-Do | Tasks also worked on / did research on | Total Hours for the week/sprint | 2023-10-30 | Hours | 2023-10-31 | Hours | 2023-11-01 | Hours | 2023-11-02 | Hours | 2023-11-03 | Hours | 2023-11-04 | Hours | 2023-11-05 | Hours
Polish up the Grant dashboard page | Completed | Alex | Tasks 2,3,5,6,7,16 | Tasks 1 | 13 | Fixed the filter functionality for the datagrid (Only filtered rows are exported if a filter is applied, otherwise all rows are exported) Made the documentation for the Think Aloud for Sprint 3 | 3 | Capstone Class/Meeting Time Performed Think Aloud With Finch Team (Made adjustments to the Think Aloud Document) Discussed different ideas on how the grant show page could potentially be implemented | 4 | Talked with Chase and fixed the small error with the filter component Worked on the Powerpoint for the Sprint 3 Demo Worked on correcting and finishing all Sprint 3 Documentation | 4 | Capstone Class/Meeting Time | 2
Make a progress bar on dashboard page (as a visual) for time spent on a grant | Completed | Chase | Tasks 4,8,15,20 | Task 1, 18 | 14 | Updated Calendar component to pull from db Added GrantShow to main, incorporated calendar component | 3 | Capstone Class/Meeting Time Discussed different ideas on how the grant show page could potentially be implemented Worked on calander component (rendering start and end dates from database) | 4 | Talked with Alex and fixed the small error with the filter component Worked on the Powerpoint for the Sprint 3 Demo | 2 | Capstone Class/Meeting Time Set up change password page, nearly finished with functionality | 5
Make a progress bar on dashboard (as a visual) for money spent on a grant | Completed | Daron | Tasks 11,12,14,15 | Task 1, 18, 22 | 12 | Updated the main grant component to pull data from the grant list api/db | 3 | Capstone Class/Meeting Time Made an on row click component Discussed different ideas on how the grant show page could potentially be implemented | 4 | Worked on deleting a grant on the grant show page. | 3 | Capstone Class/Meeting Time | 2
Get the Calander View set up | Completed | Ken | Tasks 14,15,21 | Task 1,3, 8 | 24 |  |  | Capstone Class/Meeting Time Discussed different ideas on how the grant show page could potentially be implemented Worked on creating a Modal for the grant show page feature Created additional tabs for the grant show page | 9 | Worked on updating the layout of the grant dashboard page (Made it cleaner and user friendly), refactored entire frontend | 8 | Capstone Class/Meeting Time, added controller methods for employee | 5 | controller methods for bridge entities | 2
Make datagrid be able to be exported/downloaded as an CSV file | Completed
Make datagrid be able to be exported/downloaded as an Excel file | Completed
Make filter functionality work for the exporting of CSV and Excel datagrids | Completed
Work on creating an initial grant show page | Completed
Work on a employee information page | Not started
Work on a report page | Not started
Create a new grant (Displayed on grant dashboard) | In progress
Editing an existing grant or newely created grant | In progress
Create a view transaction page | Not started
Work on making changes to the database and implementing those changes | Completed
Work on fixing the API issues and making additions/changes wherever necessary | Completed
Working on making a feature on the grant dashboard to remove and re-add columns from being viewed | Completed
Add A Pie Chart visual so that transaction/balance can be viewed | Not started
Make data come from database instead of being hardcoded for the grant dashboard | Completed
In the backend, work on JWT tokens related to the User | Completed But Scrapped
Get the Calender to use start and end dates from the database instead of being hardcoded | In progress
Work on creating a modal so that when a user clicks on a row containing a grant it takes them to a show page for that specific grant | Completed
Deleting a Grant | In progress

## Week of 1023
Tasks Sprint 3 | Status of Task | Members | Tasks To-Do | Tasks also worked on / did research on | Total Hours for the week/sprint | 2023-10-23 | Hours | 2023-10-24 | Hours | 2023-10-25 | Hours | 2023-10-26 | Hours | 2023-10-27 | Hours | 2023-10-28 | Hours | 2023-10-29 | Hours
Polish up the Grant dashboard page | Completed | Alex | Tasks 2,3,5,6,7,16 | Tasks 1 | 14.5 | Researched filter functionality in terms of exporting only specific rows as a CSV/Excel file instead of the entire datagird) | 1 | Scheduled Capstone Meeting Time Meeting with Corinne Worked on documentation for Sprint 3 (Goals) | 3.5 | Worked on getting all Sprint 3 Progress Check documentation in order | 1 | Scheduled Capstone Meeting Time Worked on trying to incorporate a filter functionality that works with the CSV / Excel File export feature | 3 |  |  | Worked on trying to add filter functionality to Excel / CSV export feature (Fixed the filter button but filtered rows do not export and instead all rows are exported) | 4 | Fixed an issue with a useState related to the filter feature (but exporting filtered rows still not functional) Added a feature to the datagrid to allow a user to remove columns from being viewed and add them back Added a global filter to the datagrid for conveniance | 2
Make a progress bar on dashboard page (as a visual) for time spent on a grant | Completed | Chase | Tasks 4,15 | Task 1 | 9 | made calendar component to render start/end date for GrantView | 1.5 | Scheduled Capstone Meeting Time Meeting with Corinne | 3 |  |  | Scheduled Capstone Meeting Time | 1 |  |  | Created GrantShow page, Tabs component, generated with garbage date and verified functionality | 2.5 | Merging multiple branches to main, testing for issues Reconfiguring grant-show page | 1
Make a progress bar on dashboard (as a visual) for money spent on a grant | Completed | Daron | Tasks 11,14,15 | Task | 12 | Worked on implementing JWT encod- ing/decoding to verify users Working on reformatting apis to the new models | 4 | Scheduled Capstone Meeting Time Meeting with Corinne Worked on implementing JWT encod- ing/decoding to verify users | 3 |  |  | Scheduled Capstone Meeting Time | 1 |  |  |  |  | Finished grant api Rendered real data to the main grant dashboard | 4
Get the Calander View set up | Completed | Ken | Tasks 14,15 | Task | 9 |  |  | Scheduled Capstone Meeting Time Meeting with Corinne, planning website design given Corinne's feedback | 4 | Combining branches to fix state of main | 2 | Scheduled Capstone Meeting Time, continuing fixing up main | 3
Make datagrid be able to be exported/downloaded as an CSV file | Completed
Make datagrid be able to be exported/downloaded as an Excel file | Completed
Make filter functionality work for the exporting of CSV and Excel datagrids | Completed
Work on creating an initial grant show page | Completed
Work on a employee information page | Not started
Work on a report page | Not started
Create a new grant (Displayed on grant dashboard) | In progress
Editing an existing grant or newely created grant | In progress
Create a view transaction page | Not started
Work on making changes to the database and implementing those changes | Completed
Work on fixing the API issues and making additions/changes wherever necessary | Completed
Working on making a feature on the grant dashboard to remove and re-add columns from being viewed | Completed
Add A Pie Chart visual so that transaction/balance can be viewed | Not started
Make data come from database instead of being hardcoded for the grant dashboard | Completed
In the backend, work on JWT tokens related to the User | Completed But Scrapped
Get the Calender to use start and end dates from the database instead of being hardcoded | In progress
Work on creating a modal so that when a user clicks on a row containing a grant it takes them to a show page for that specific grant | Completed
Deleting a Grant | In progress

## Week of 1016
Tasks Sprint 3 | Status of Task | Members | Tasks that need to be done | Tasks also worked on / did research on | Total Hours for the week/sprint | 2023-10-16 | Hours | 2023-10-17 | Hours | 2023-10-18 | Hours | 2023-10-19 | Hours | 2023-10-20 | Hours | 2023-10-21 | Hours | 2023-10-22 | Hours
Polish up dashboard page, make data come from database instead of being hard-coded | In progress | Alex | Tasks 2,3,5 | Tasks 1 | 14.5 |  |  |  |  | Spent time talking about features and delegating those features between ourselves. | 2 | Scheduled Capstone Meeting Time Worked on timesheet | 4.5 | Did research on DataChart Tools and the Datachart Excel Export/CSV Export Feature | 2.5 | Work on implentation of datachart excel export feature Worked on implementation of datachart CSV export feature | 5.5
Make a progress bar on dashboard page (as a visual) for time spent on a grant | Completed | Chase | Tasks 4 | Task 1 | 13.5 | Continuing work on Calendar Page getting 6 month calendar view working set up new week in timesheet | 6 |  |  | got 6 month view working Spent time talking about features and delegating those features between ourselves. | 3.5 | Scheduled Capstone Meeting Time worked on wireframes, db rearranging | 4
Make a progress bar on dashboard (as a visual) for money spent on a grant | In progress | Daron | Tasks | Task | 12 |  |  |  |  | Spent time talking about features and delegating those features between ourselves. | 2 | Scheduled Capstone Meeting Time Worked on wireframes and page layout with Ken | 5 | Made the create API route for Grant, Employee/PI Started creating multistep form for creating a new grant | 5
Get the Calander View set up | In progress | Ken | Tasks | Task | 13 |  |  |  |  | Created all tickets. Spent time talking about features and delegating those features between ourselves. | 3 | Scheduled Capstone Meeting Time | 6 | Redid database again due to Corinne's feedback | 4
Make tables be able to be exported/downloaded as an Excel file | Completed
Work on a grant information page | In progress
Work on a employee information page | In progress
Work on a report page | In progress
Create a new grant (on dashboard) | In progress
Editing an existing grant or newely created grant | In progress
Create a view transaction page | In progress

## Week of 109
Members | 2023-10-09 | Hours | 2023-10-10 | Hours | 2023-10-11 | Hours | 2023-10-12 | Hours | 2023-10-13 | Hours | 2023-10-14 | Hours | 2023-10-15 | Hours | Total Hours for the week/sprint | Tasks Sprint 2 | Status of Task
Alex | Helped Daron Fix a minor backend issue. Worked on getting documenation fixed for Think Aloud | 1 | Scheduled Capstone Meeting Time Worked on documentation for Think Aloud Performed Think Aloud with Finch Team Worked on finalizing database design | 4 | Worked on finalizing all documentation for Sprint 2 Made Sprint 2 Powerpoint Presentation Completed Team Reflection Survey | 3.5 | Scheduled Capstone Meeting Time | 2 | [6 empty] | 10.5 | Install .NET and make sure it is working | Completed But Scrapped
Chase |  |  | Scheduled Capstone Meeting Time Performed Think Aloud with Finch Team Worked on finalizing database design | 3 | Completed Team Reflection Survey | 1 | Scheduled Capstone Meeting Time | 2 |  |  |  |  | Merged main into chase-dev continued work on calendar view | 1 | 7 | Talk and determine goals for sprint 2 | Completed
Daron | Finished Express backend. Finished register and login api. Connected with frontend pages and tested all edge cases. Tried a few different state management solution with react. | 5 | Scheduled Capstone Meeting Time Performed Think Aloud with Finch Team Fixed navigation for register and login pages | 3 | Completed Team Reflection Survey Worked on implementing user contexts and fixing the logout feature | 3 | Scheduled Capstone Meeting Time | 2 | [6 empty] | 13 | Meet with Corinne to learn more about the project and what she is looking for. | Completed
Ken |  |  | Scheduled Capstone Meeting Time ThinkAloud with Finch team Worked on finalizing database design | 3 | New database design plantUML integration Completed Team Reflection Survey | 1 | Scheduled Capstone Meeting Time | 2 |  |  | Planning website design | 3 |  |  | 9 | Create More Wireframes | In progress
[16 empty] | Fix Initial .NET/Database issue | Completed But Scrapped
[16 empty] | Create the timesheet for Sprint 2 for documentation purposes | Completed
[16 empty] | Practice React | In progress
[16 empty] | Try to implement chart feature | Completed
[16 empty] | Try to implement download chart feature | Completed
[16 empty] | Get Rails Backend Installed. (Remove all files related to .NET) | Completed But Scrapped
[16 empty] | Get Rails Backend working with PSQL | Completed But Scrapped
[16 empty] | Make sure that Rails is working for everyone | Scrapped
[16 empty] | Polish up dashboard page, make data come from database instead of being hard-coded | In progress
[16 empty] | Make sidebar components link to other pages | Completed
[16 empty] | Get Express Typescript Installed (Remove all files to Rails and Dotnet | Completed
[16 empty] | Get Express Typescript backend working with database | Completed
[16 empty] | Make sure that Express Typescript backend works for everyone | Completed
[16 empty] | Work on User Registration | Completed
[16 empty] | Work on user login | Completed
[16 empty] | Work on user context | Completed

## Week of 102
Members | 2023-10-02 | Hours | 2023-10-03 | Hours | 2023-10-04 | Hours | 2023-10-05 | Hours | 2023-10-06 | Hours | 2023-10-07 | Hours | 2023-10-08 | Hours | Total Hours for the week/sprint
Alex |  |  | Scheduled Capstone Meeting Time Met with Corrine Fixed Small Bug in BarChart Addition | 2.5 | Worked on gathering and fixing all documentation for the Sprint 2 Progress Check | 2 | Scheduled Capstone Meeting Time set up charts view page | 6 |  |  | Worked on a feature for downloading charts as a pdf (Completed) | 2 |  |  | 12.5
Chase | Confirmed meeting with Corinne for Tuesday Setup Timesheet for this week more frontend React development | 1 | Scheduled Capstone Meeting Time Met with Corrine | 2 | Continued work on Calendar page reviewed annotations of data provided by Corinne |  | Scheduled Capstone Meeting Time worked on setting up database UML | 6 | [6 empty] | 9
Daron |  |  | Scheduled Capstone Meeting Time Met with Corrine | 2 | began setting up Rails backend and started working on user auth | 4 | Scheduled Capstone Meeting Time set up Express backend | 6 |  |  | Prisma db research and integration with Ken | 2.5 |  |  | 14.5
Ken | research prod dbs servers | 0.5 | Scheduled Capstone Meeting Time Met with Corrine | 2 |  |  | Scheduled Capstone Meeting Time | 2 |  |  | Prisma db research and integration with Daron | 2.5 | reviewed corinne's documents and watched tutorials in typescript backend | 2 | 9

## Week of 925
Members | 2023-09-25 | Hours | 2023-09-26 | Hours | 2023-09-27 | Hours | 2023-09-28 | Hours | 2023-09-29 | Hours | 2023-09-30 | Hours | 2023-10-01 | Hours | Total Hours for the week/sprint
Alex | Worked on setting up dev environment on WSL (ran into database issue) | 1 | Class and Scheduled Meeting Worked on setting up dev environment on Windows due to error on WSL Worked on wireframes | 2.5 | Worked on fixing PostgreSQL issue on Windows (Fixed) | 5.5 | Class and Scheduled Meeting | 2 |  |  | Researched React graphs through the use of Tailwind and ChartJS | 1 | Work on Adding chart Feature to Project (Ran into ID error) | 1 | 13
Chase |  |  | Class and Scheduled Meeting Worked on setting up dev environ | 2 | Updated documentation Set up dev env | 1 | Class and Scheduled Meeting FINALLY got dev env set up more research on React | 3 |  |  | set up home dev env React practice adding link functionality to Sidebar component | 3 |  |  | 9
Daron |  |  | Class and Scheduled Meeting | 2 | Fix .NET Database Issues (Fixed) | 7 | Class and Scheduled Meeting | 2 | [6 empty] | 11
Ken |  |  | Class and Scheduled Meeting | 2 | Helped Alex get DB issue figured out | 3 | Class and Scheduled Meeting | 2 |  |  | research prod dbs servers | 2 |  |  | 9

## Week of 918 - End of Sprint 1
| 2023-09-18 | Hours | 2023-09-19 | Hours | 2023-09-20 | Hours | 2023-09-21 | Hours | 2023-09-22 | Hours | 2023-09-23 | Hours | 2023-09-24 | Hours | Total Hours for the week/sprint | Tasks for Sprint 1 | Status of Task
Alex |  | 0 | - Progress Check/Scheduled Meeting 2 hours | 2 | Collect and fix all documentation. Submit documentation to Github Repo Completed Team Reflection Survey 3.5 hours | 3.5 | Demo Day/Scheduled Meeting 2 hours | 2 |  |  |  |  | Watched tutorial for .Net | 1.5 | 9 | Installing React and making sure that it works correctly | Completed
Chase |  | 0 | - Progress Check/Scheduled Meeting - set up meeting with POC - began working on Demo Slides 4 hours | 4 | finish demo presentation set up meeting with POC Completed Team Reflection Survey 2.5 hours | 2.5 | Demo Day/Scheduled Meeting 2 hours | 2 |  |  |  |  | set up development environment | 1 | 9.5 | Talking and working on Team Contract | Completed
Daron | - Implement .NET backend - Discuss backend tech with Ken - Work on grid/homepage 4 hours | 4 | - Progress Check/Scheduled Meeting 2 hours | 2 | finish demo presentation Completed Team Reflection Survey 1.5 hours | 1.5 | Demo Day/Scheduled Meeting 2 hours | 2 | [6 empty] | 9.5 | Meeting with the customer | In progress
Ken | database plantUML, planning, discussing backend tech with Daron 3 hours | 3 | - Progress Check/Scheduled Meeting 2 hours | 2 | .net/database connection work Completed Team Reflection Survey 1.5 hours | 1.5 | Demo Day/Scheduled Meeting 2 hours | 2 | [6 empty] | 8.5 | Creating Github Repo | Completed
[16 empty] | Work on making basic wireframes using Balsamiq (Learning how to use Balsamiq) | Completed
[16 empty] | Create the timesheet for documentation purposes | Completed
[16 empty] | Figure out which Backend Framework/API we will use | Completed
[16 empty] | Figure out which database we will use | In progress
[16 empty] | Create discord server(communication), google calender (important dates), and trello board (keeping track of important elements) | Completed
[16 empty] | Make a rough sketch of the database design | Completed
[16 empty] | Implement backend .NET | Completed
[16 empty] | Implement database to work with .NET | In progress

## Week of 911
Members | 2023-09-11 | Hours | 2023-09-12 | Hours | 2023-09-13 | Hours | 2023-09-14 | Hours | 2023-09-15 | Hours | 2023-09-16 | Hours | 2023-09-17 | Hours | Total Hours for the week/sprint
Alex |  | 0 | Completed Task 2 (Team Contract) - 1 hour Research how to do Task 1 - 0.5 hours | 1.5 | Completed Task 1 (Get React working) - 1 hour Work on making the timesheet (Task 6) - 1 hours Fiddle with Balsmiq for making wireframes (Task 5) - 1 hour | 3 | Went to group meeting Figured out which Backend Framework/API we will use (Task 7) Figured out which database we will use (Task 8) Working on a rough sketch database design (Task 10) 2 hours | 2 |  | 0 |  | 0 | Spent some time watching videos about using React 1.5 hours | 1.5 | 8
Chase |  | 0 | Completed Task 2 (Team Contract) - 1 hour Worked on Task 3 (Email with customer) - 0.5 Hours Completed Task 10 (Discord,Trello, Google Calander) - 0.5 Hours | 2 | Fiddle with Balsamiq for wireframes (Task 5) - 1 hour Made some finishing touchs on the timesheet (Task 6) - 0.5 hours | 1.5 | Went to group meeting Figured out which Backend Framework/API we will use (Task 7) Figured out which database we will use (Task 8) Working on a rough sketch of database design (Task 10) 2 hours | 2 |  | 0 |  | 0 | Spent time researching and learning about React 1.5 hours | 1.5 | 7
Daron |  | 0 | Task 1 - Already done (0 hours) Completed Task 2 (Team Contract) - 1 hour Implemented React and Made Github Repo (Task 4) - 1 hour | 2 | Make Balsamiq Cloud for group. Fiddle with Balsamiq for wireframes. Make a few design wireframes (Task 5) - 1 hour | 1 | Went to group meeting Figured out which Backend Framework/API we will use (Task 7) - 1 hour Figured out which database we will use (Task 8) - 1hour Working on a rough sketch of database design (Task 10) 2 hours Research backends (Task 10) - 1 hour Research databases that can work with backends(Task 11) - 1 hour | 4 | Research and Experiment with Rails/Flask backend 1.5 hours | 1.5 | Research and Experiment with .NET backend 1 hour | 1 | Created the initial grid for the homepage and generated fake data to fill it for now - 1 hour | 1 | 10.5
Ken |  | 0 | Task 1 - Already done (0 hours) Completed task 2 (Team Contract) - 1 hour | 1 | Researched database design (Task 10) - 1 hour | 1 | Went to group meeting Figured out which Backend Framework/API we will use (Task 7) Figured out which database we will use (Task 8) Working on the database design (Task 10) 2 hours Research databases that can work with backends (Task 11) - 1 hour | 3 |  | 0 | React training: https://legacy.reactjs.org/tutorial/tutorial.html 1 hour | 1 | Database planning, backend discussing with Daron, .NET training videos 2 hours | 2 | 8