## Week of 911
Members | 2023-09-11 | Hours | 2023-09-12 | Hours | 2023-09-13 | Hours | 2023-09-14 | Hours | 2023-09-15 | Hours | 2023-09-16 | Hours | 2023-09-17 | Hours | Total Hours for the week/sprint
Alex |  | 0 | Completed Task 2 (Team Contract) - 1 hour Research how to do Task 1 - 0.5 hours | 1.5 | Completed Task 1 (Get React working) - 1 hour Work on making the timesheet (Task 6) - 1 hours Fiddle with Balsmiq for making wireframes (Task 5) - 1 hour | 3 | Went to group meeting Figured out which Backend Framework/API we will use (Task 7) Figured out which database we will use (Task 8) Working on a rough sketch database design (Task 10) 2 hours | 2 |  | 0 |  | 0 | Spent some time watching videos about using React 1.5 hours | 1.5 | 8
Chase |  | 0 | Completed Task 2 (Team Contract) - 1 hour Worked on Task 3 (Email with customer) - 0.5 Hours Completed Task 10 (Discord,Trello, Google Calander) - 0.5 Hours | 2 | Fiddle with Balsamiq for wireframes (Task 5) - 1 hour Made some finishing touchs on the timesheet (Task 6) - 0.5 hours | 1.5 | Went to group meeting Figured out which Backend Framework/API we will use (Task 7) Figured out which database we will use (Task 8) Working on a rough sketch of database design (Task 10) 2 hours | 2 |  | 0 |  | 0 | Spent time researching and learning about React 1.5 hours | 1.5 | 7
Daron |  | 0 | Task 1 - Already done (0 hours) Completed Task 2 (Team Contract) - 1 hour Implemented React and Made Github Repo (Task 4) - 1 hour | 2 | Make Balsamiq Cloud for group. Fiddle with Balsamiq for wireframes. Make a few design wireframes (Task 5) - 1 hour | 1 | Went to group meeting Figured out which Backend Framework/API we will use (Task 7) - 1 hour Figured out which database we will use (Task 8) - 1hour Working on a rough sketch of database design (Task 10) 2 hours Research backends (Task 10) - 1 hour Research databases that can work with backends(Task 11) - 1 hour | 4 | Research and Experiment with Rails/Flask backend 1.5 hours | 1.5 | Research and Experiment with .NET backend 1 hour | 1 | Created the initial grid for the homepage and generated fake data to fill it for now - 1 hour | 1 | 10.5
Ken |  | 0 | Task 1 - Already done (0 hours) Completed task 2 (Team Contract) - 1 hour | 1 | Researched database design (Task 10) - 1 hour | 1 | Went to group meeting Figured out which Backend Framework/API we will use (Task 7) Figured out which database we will use (Task 8) Working on the database design (Task 10) 2 hours Research databases that can work with backends (Task 11) - 1 hour | 3 |  | 0 | React training: https://legacy.reactjs.org/tutorial/tutorial.html 1 hour | 1 | Database planning, backend discussing with Daron, .NET training videos 2 hours | 2 | 8

## Week of 918
Tasks | Status of Task | Members | Tasks that need to be done | Tasks also worked on / did research on | Total Hours for the week/sprint | 2023-09-18 | Hours | 2023-09-19 | Hours | 2023-09-20 | Hours | 2023-09-21 | Hours | 2023-09-22 | Hours | 2023-09-23 | Hours | 2023-09-24 | Hours
Installing React and making sure that it works correctly | Completed | Alex | Task 1,2,6 | Task 5,7,8,10 | 7.5 |  | 0 | - Progress Check/Scheduled Meeting 2 hours | 2 | Collect and fix all documentation. Submit documentation to Github Repo Completed Team Reflection Survey 3.5 hours | 3.5 | Demo Day/Scheduled Meeting 2 hours | 2
Talking and working on Team Contract | Completed | Chase | Task 1,2,3,9 | Task 5,6,7,8,10 | 8.5 |  | 0 | - Progress Check/Scheduled Meeting - set up meeting with POC - began working on Demo Slides 4 hours | 4 | finish demo presentation set up meeting with POC Completed Team Reflection Survey 2.5 hours | 2.5 | Demo Day/Scheduled Meeting 2 hours | 2
Meeting with the customer | In progress | Daron | Task 1,2,4,11 | Task 5,7,8,9 | 9.5 | - Implement .NET backend - Discuss backend tech with Ken - Work on grid/homepage 4 hours | 4 | - Progress Check/Scheduled Meeting 2 hours | 2 | finish demo presentation Completed Team Reflection Survey 1.5 hours | 1.5 | Demo Day/Scheduled Meeting 2 hours | 2
Creating Github Repo | Completed | Ken | Task 1,2,10 | Task 7,8,12 | 8.5 | database plantUML, planning, discussing backend tech with Daron 3 hours | 3 | - Progress Check/Scheduled Meeting 2 hours | 2 | .net/database connection work Completed Team Reflection Survey 1.5 hours | 1.5 | Demo Day/Scheduled Meeting 2 hours | 2
Work on making basic wireframes using Balsamiq (Learning how to use Balsamiq) | Completed
Create the timesheet for documentation purposes | Completed
Figure out which Backend Framework/API we will use | Completed
Figure out which database we will use | In progress
Create discord server(communication), google calender (important dates), and trello board (keeping track of important elements) | Completed
Make a rough sketch of the database design | Completed
Implement backend .NET | Completed
Implement database to work with .NET | In progress