## Current Week
Tasks Sprint 2 | Status of Task | Members | Tasks that need to be done | Tasks also worked on / did research on | Total Hours for the week/sprint | 2023-10-09 | Hours | 2023-10-10 | Hours | 2023-10-11 | Hours | 2023-10-12 | Hours | 2023-10-13 | Hours | 2023-10-14 | Hours | 2023-10-15 | Hours
Install .NET and make sure it is working | Completed But Scrapped | Alex | Tasks 1,2,3,7,12, 17 | Tasks 4,6,8,9 | 9.5 | Helped Daron Fix a minor backend issue. Worked on getting documenation fixed for Think Aloud | 1 | Scheduled Capstone Meeting Time Worked on documentation for Think Aloud Performed Think Aloud with Finch Team Worked on finalizing database design | 4 | Worked on finalizing all documentation for Sprint 2 Made Sprint 2 Powerpoint Presentation Completed Team Reflection Survey | 2.5 | Scheduled Capstone Meeting Time | 2
Talk and determine goals for sprint 2 | Completed | Chase | Tasks 1,2,3,7,12, 17 | Task 6,14 | 6 |  |  | Scheduled Capstone Meeting Time Performed Think Aloud with Finch Team Worked on finalizing database design | 3 | Completed Team Reflection Survey | 1 | Scheduled Capstone Meeting Time | 2
Meet with Corinne to learn more about the project and what she is looking for. | Completed | Daron | Tasks 2,3,5,10,12,15,16,17,18,19 | Task 5, 20, 19, 21 | 13 | Finished Express backend. Finished register and login api. Connected with frontend pages and tested all edge cases. Tried a few different state management solution with react. | 5 | Scheduled Capstone Meeting Time Performed Think Aloud with Finch Team Fixed navigation for register and login pages | 3 | Completed Team Reflection Survey Worked on implementing user contexts and fixing the logout feature | 3 | Scheduled Capstone Meeting Time | 2
Create More Wireframes | In progress | Ken | Tasks 2,3,5,11,12, 17 | Task 5,10 | 12 |  |  | Scheduled Capstone Meeting Time ThinkAloud with Finch team Worked on finalizing database design | 3 | New database design plantUML integration Completed Team Reflection Survey | 1 | Scheduled Capstone Meeting Time | 2 |  |  | Dashboard page | 6
Fix Initial .NET/Database issue | Completed But Scrapped
Create the timesheet for Sprint 2 for documentation purposes | Completed
Practice React | In progress
Try to implement chart feature | Completed
Try to implement download chart feature | Completed
Get Rails Backend Installed. (Remove all files related to .NET) | Completed But Scrapped
Get Rails Backend working with PSQL | Completed But Scrapped
Make sure that Rails is working for everyone | Scrapped
Polish up dashboard page, make data come from database instead of being hard-coded | In progress
Make sidebar components link to other pages | Completed
Get Express Typescript Installed (Remove all files to Rails and Dotnet | Completed
Get Express Typescript backend working with database | Completed
Make sure that Express Typescript backend works for everyone | Completed
Work on User Registration | Completed
Work on user login | Completed
Work on user context | Completed

## Week of 102
Members | 2023-10-02 | Hours | 2023-10-03 | Hours | 2023-10-04 | Hours | 2023-10-05 | Hours | 2023-10-06 | Hours | 2023-10-07 | Hours | 2023-10-08 | Hours | Total Hours for the week/sprint
Alex |  |  | Scheduled Capstone Meeting Time Met with Corrine Fixed Small Bug in BarChart Addition | 2.5 | Worked on gathering and fixing all documentation for the Sprint 2 Progress Check | 2 | Scheduled Capstone Meeting Time set up charts view page | 6 |  |  | Worked on a feature for downloading charts as a pdf (Completed) | 2 |  |  | 12.5
Chase | Confirmed meeting with Corinne for Tuesday Setup Timesheet for this week more frontend React development | 1 | Scheduled Capstone Meeting Time Met with Corrine | 2 | Continued work on Calendar page reviewed annotations of data provided by Corinne |  | Scheduled Capstone Meeting Time worked on setting up database UML | 6 | [6 empty] | 9
Daron |  |  | Scheduled Capstone Meeting Time Met with Corrine | 2 | began setting up Rails backend and started working on user auth | 4 | Scheduled Capstone Meeting Time set up Express backend | 6 |  |  | Prisma db research and integration with Ken | 2.5 |  |  | 14.5
Ken | research prod dbs servers | 0.5 | Scheduled Capstone Meeting Time Met with Corrine | 2 |  |  | Scheduled Capstone Meeting Time | 2 |  |  | Prisma db research and integration with Daron | 2.5 | reviewed corinne's documents and watched tutorials in typescript backend | 2 | 9

## Week of 925
Members | 2023-09-25 | Hours | 2023-09-26 | Hours | 2023-09-27 | Hours | 2023-09-28 | Hours | 2023-09-29 | Hours | 2023-09-30 | Hours | 2023-10-01 | Hours | Total Hours for the week/sprint
Alex | Worked on setting up dev environment on WSL (ran into database issue) | 1 | Class and Scheduled Meeting Worked on setting up dev environment on Windows due to error on WSL Worked on wireframes | 2.5 | Worked on fixing PostgreSQL issue on Windows (Fixed) | 5.5 | Class and Scheduled Meeting | 2 |  |  | Researched React graphs through the use of Tailwind and ChartJS | 1 | Work on Adding chart Feature to Project (Ran into ID error) | 1 | 13
Chase |  |  | Class and Scheduled Meeting Worked on setting up dev environ | 2 | Updated documentation Set up dev env | 1 | Class and Scheduled Meeting FINALLY got dev env set up more research on React | 3 |  |  | set up home dev env React practice adding link functionality to Sidebar component | 3 |  |  | 9
Daron |  |  | Class and Scheduled Meeting | 2 | Fix .NET Database Issues (Fixed) | 7 | Class and Scheduled Meeting | 2 | [6 empty] | 11
Ken |  |  | Class and Scheduled Meeting | 2 | Helped Alex get DB issue figured out | 3 | Class and Scheduled Meeting | 2 |  |  | research prod dbs servers | 2 |  |  | 9

## Week of 918 - End of Sprint 1
| 2023-09-18 | Hours | 2023-09-19 | Hours | 2023-09-20 | Hours | 2023-09-21 | Hours | 2023-09-22 | Hours | 2023-09-23 | Hours | 2023-09-24 | Hours | Total Hours for the week/sprint | Tasks for Sprint 1 | Status of Task
Alex |  | 0 | - Progress Check/Scheduled Meeting 2 hours | 2 | Collect and fix all documentation. Submit documentation to Github Repo Completed Team Reflection Survey 3.5 hours | 3.5 | Demo Day/Scheduled Meeting 2 hours | 2 |  |  |  |  | Watched tutorial for .Net | 1.5 | 9 | Installing React and making sure that it works correctly | Completed
Chase |  | 0 | - Progress Check/Scheduled Meeting - set up meeting with POC - began working on Demo Slides 4 hours | 4 | finish demo presentation set up meeting with POC Completed Team Reflection Survey 2.5 hours | 2.5 | Demo Day/Scheduled Meeting 2 hours | 2 |  |  |  |  | set up development environment | 1 | 9.5 | Talking and working on Team Contract | Completed
Daron | - Implement .NET backend - Discuss backend tech with Ken - Work on grid/homepage 4 hours | 4 | - Progress Check/Scheduled Meeting 2 hours | 2 | finish demo presentation Completed Team Reflection Survey 1.5 hours | 1.5 | Demo Day/Scheduled Meeting 2 hours | 2 | [6 empty] | 9.5 | Meeting with the customer | In progress
Ken | database plantUML, planning, discussing backend tech with Daron 3 hours | 3 | - Progress Check/Scheduled Meeting 2 hours | 2 | .net/database connection work Completed Team Reflection Survey 1.5 hours | 1.5 | Demo Day/Scheduled Meeting 2 hours | 2 | [6 empty] | 8.5 | Creating Github Repo | Completed
[16 empty] | Work on making basic wireframes using Balsamiq (Learning how to use Balsamiq) | Completed
[16 empty] | Create the timesheet for documentation purposes | Completed
[16 empty] | Figure out which Backend Framework/API we will use | Completed
[16 empty] | Figure out which database we will use | In progress
[16 empty] | Create discord server(communication), google calender (important dates), and trello board (keeping track of important elements) | Completed
[16 empty] | Make a rough sketch of the database design | Completed
[16 empty] | Implement backend .NET | Completed
[16 empty] | Implement database to work with .NET | In progress

## Week of 911
Members | 2023-09-11 | Hours | 2023-09-12 | Hours | 2023-09-13 | Hours | 2023-09-14 | Hours | 2023-09-15 | Hours | 2023-09-16 | Hours | 2023-09-17 | Hours | Total Hours for the week/sprint
Alex |  | 0 | Completed Task 2 (Team Contract) - 1 hour Research how to do Task 1 - 0.5 hours | 1.5 | Completed Task 1 (Get React working) - 1 hour Work on making the timesheet (Task 6) - 1 hours Fiddle with Balsmiq for making wireframes (Task 5) - 1 hour | 3 | Went to group meeting Figured out which Backend Framework/API we will use (Task 7) Figured out which database we will use (Task 8) Working on a rough sketch database design (Task 10) 2 hours | 2 |  | 0 |  | 0 | Spent some time watching videos about using React 1.5 hours | 1.5 | 8
Chase |  | 0 | Completed Task 2 (Team Contract) - 1 hour Worked on Task 3 (Email with customer) - 0.5 Hours Completed Task 10 (Discord,Trello, Google Calander) - 0.5 Hours | 2 | Fiddle with Balsamiq for wireframes (Task 5) - 1 hour Made some finishing touchs on the timesheet (Task 6) - 0.5 hours | 1.5 | Went to group meeting Figured out which Backend Framework/API we will use (Task 7) Figured out which database we will use (Task 8) Working on a rough sketch of database design (Task 10) 2 hours | 2 |  | 0 |  | 0 | Spent time researching and learning about React 1.5 hours | 1.5 | 7
Daron |  | 0 | Task 1 - Already done (0 hours) Completed Task 2 (Team Contract) - 1 hour Implemented React and Made Github Repo (Task 4) - 1 hour | 2 | Make Balsamiq Cloud for group. Fiddle with Balsamiq for wireframes. Make a few design wireframes (Task 5) - 1 hour | 1 | Went to group meeting Figured out which Backend Framework/API we will use (Task 7) - 1 hour Figured out which database we will use (Task 8) - 1hour Working on a rough sketch of database design (Task 10) 2 hours Research backends (Task 10) - 1 hour Research databases that can work with backends(Task 11) - 1 hour | 4 | Research and Experiment with Rails/Flask backend 1.5 hours | 1.5 | Research and Experiment with .NET backend 1 hour | 1 | Created the initial grid for the homepage and generated fake data to fill it for now - 1 hour | 1 | 10.5
Ken |  | 0 | Task 1 - Already done (0 hours) Completed task 2 (Team Contract) - 1 hour | 1 | Researched database design (Task 10) - 1 hour | 1 | Went to group meeting Figured out which Backend Framework/API we will use (Task 7) Figured out which database we will use (Task 8) Working on the database design (Task 10) 2 hours Research databases that can work with backends (Task 11) - 1 hour | 3 |  | 0 | React training: https://legacy.reactjs.org/tutorial/tutorial.html 1 hour | 1 | Database planning, backend discussing with Daron, .NET training videos 2 hours | 2 | 8